## Slide 1: M&S – HK O365 Migration
Notes: Kindly follow the guidelines mentioned in the notes section of every slide.
EIT General Presentation Guidelines – Do’s and Don’ts
Do’s
Title and Agenda Slides are mandatory for every presentation.
Use only the predefined slide layouts.
Use more pictures, graphs and high quality graphics while limiting text.
Keep the assigned space between text, graphics, tables.
Split and move content to a new slide in case it does not fit into a single slide.
Use transitions and animations only if the subject matter requires it.
Arrange slides as per the stated Agenda.
Insert a Thank You slide at the end.
Don’ts
Change the Master Title slide.
Place any content over master title slide image.
Change font type, size, color, alignment.
Change Line spacing or apply shadows to text.
Clutter the slide with too much text.
Overuse animations or transitions.
Change bullet styles.
Edit slide master.
Change slide background.
Change logos.
Modify slide footer.
Overlap text or any illustrations on Al-Futtaim brand logos.

## Slide 2: Agenda
Information Required
Architecture
Migration Steps
Key Considerations
Tasks
Risks
Reports Required

## Slide 3: Information Required for Migration
  The following information is required for estimating the migration timelines and finalizing the plan
    Mail domains in use by affected users.
    Current Internet Bandwidth at M&S HK
    Client devices in use
    Mailbox size, SharePoint and OneDrive Statistics
    Email send/receive limits.
    Room mailboxes, Shared mailboxes, Distribution/Security groups, Rules specific to the domain and SMTP Relays.
    DLP Rules, Spam filtering and malware settings, OOF settings per mailbox.
    Default language used in Mailboxes.
    Mail forwarding settings, mailbox permissions specifically assigned by users if any.

## Slide 4: Architecture

## Slide 5: Migration Steps
Add navya.co.id
As accepted domain in onpremise AD.
.
Export user details from Navya O365 Tenant
Create 1 test user
To performing tests
Finalize Cutover
Date
Perform Beta
(
Actual Users
)
for
test and revert to
original
Cutover Day
Initiate the
Production users
migration in
Batches
Perform post
-
migration tasks
,
Configure Outlook Profile once the
content migration is completed
.
Initiate Sync for
user data

## Slide 6: Key considerations
Migration
As new ID’s are being assigned to users the profile will need to be recreated on each user machine. This requires us to touch each machine. Hence a batch migration is proposed post cutover date.
Email forwarding will have to be enabled on the Source tenant for the migrated user
User Experience
User logon credentials and email domain will change.
User PST (if any) will have to be reattached to the new profile.
User outlook address cache will no longer be available.
Recurring Meetings with no end date will have to be recreated.
OneDrive and SharePoint local synchronization will have to be re-established by the user

## Slide 7: Steps for Mailbox Migration
Source Tenant :- M&S UK IT
Pre Migration
Create a source admin account and assign application Impersonation permission.
Export user list to CSV.
Provide Permission and Sharing details for Exchange Online.
Provide 5 test accounts.
Post Migration
Setup email forwarding for the users once they are migrated.
Export X500 address along with Display name.
Set Automatic reply, for all the migrated users.
Target Tenant :- AFG
Create a Target admin account and assign application Impersonation permission.
Create users in AFG AD and sync it to Office 365.
Perform migrations for Exchange Online.
Add and verify the domain and assign it to the users (UPN Suffix).
Import X500 addresses.
M&S HK IT:
Create New Outlook profile for users being migrated.
Enter new credentials in their Outlook profile. (The new profile will be completely synced from Cloud).
Password change at first logon.
Delete and recreate corrupted recurring meetings.

## Slide 8: Steps for Migration of O365 components
The following steps capture High level design for OneDrive and SharePoint Document Library migration. Others modules migration steps TBD post discovery.
Source Tenant :- M&S UK IT
Provide permission and sharing details for SharePoint and OneDrive.
SharePoint Groups and User account details.
Add administrative privileges to the OneDrive site.
Target Tenant :- AFG
Perform migration for SharePoint Online and OneDrive
Bulk creation of OneDrive for business Sites.
Add permissions and sharing information.
M&S HK IT:
Update SharePoint URL and OneDrive URL.
Re-establish OneDrive and SharePoint Local synchronization.

## Slide 9: Risks
Risk Identified | Possibility | Implications | Option to Overcome
Cutover migration | Based on the statistics and Bandwidth availability. | Network Bottleneck | Perform migration in Batches
SharePoint and OneDrive Shared Permissions | We require the list of existing permissions. | Loss of Sharing or permissions both Internal/External. | Manually apply permission.

## Slide 10: Reports Required
The following report output is required to determine the modules and volumes in use
Office 365 Activity report for all the Office 365 components individually :
  https://support.office.com/en-us/article/Activity-Reports-in-the-Office-365-admin-center-0d6dfb17-8582-4172-a9a9-aed798150263
Mailbox utilization report:
  https://blogs.technet.microsoft.com/thomas_ashworth/2012/04/11/office-365-script-get-an-office-365-user-statistics-report/

## Slide 11: Thank You